## Cover
SACRED ROAD SUPPLY
Supplier Sample Verification Tracker
Purpose: | Validate 4 high-risk SKUs with physical samples BEFORE listing them live.
Total sample budget: | ~$96 (one-time)
Timeline: | ~7 business days end-to-end (order → arrive → test → decide)
Rule: | Any MUST-PASS check fails → don't list. Try CJ-USA backup → if fails again, drop SKU.
STATUS DASHBOARD
SKU | Product | Sample Cost | Status | Decision | Decision Date | Listing Eligible?
SRS-EM-002 | Dual Dash Cam — Front + Cabin | 45 | PENDING | (awaiting test) |  | NO — verify first
SRS-EM-001 | 24V/12V USB-C Charger | 11 | PENDING | (awaiting test) |  | NO — verify first
SRS-EM-003 | Bluetooth Headset — Single Ear | 23 | PENDING | (awaiting test) |  | NO — verify first
SRS-TC-001 | Waterless Wash & Wax Kit | 17 | PENDING | (awaiting test) |  | NO — verify first
INSTRUCTIONS
1. Click each SKU's tab below to open its verification checklist.
2. Place sample orders from Zendrop (or CJ-USA if Zendrop unavailable). Log order date + arrival date.
3. Run each test. In the RESULT column, select PASS / FAIL / N/A from the dropdown.
4. Log decision + date on this Cover sheet.
5. Send the completed file back — catalog gets updated based on results.

## Dash Cam
Dual Dash Cam — Front + Cabin, Night Vision
SKU: SRS-EM-002 | Supplier: Zendrop US (primary) / CJ-USA (backup)
Sample cost: $45.00 | Sell price: $89.95
Warehouse target: CA / NJ / GA US warehouse
ORDER TRACKING
Order placed (date):
Order # / tracking:
Arrived (date):
Days from order to arrival:
Test ID | Test description | Expected pass criteria | MUST PASS? | Result | Date tested | Notes
PACKAGING & BUILD
P1 | Arrived within 5 business days of order placement | 5 days or less | YES | PENDING
P2 | Box undamaged, includes: manual, 32GB SD card, suction mount, USB-C cable, 12V/24V power adapter | All items present | YES | PENDING
P3 | No rattle when shaken; USB ports seat cleanly; mount swivel firm not loose | Solid build | — | PENDING
DAYTIME FOOTAGE
D1 | Front: license plates readable at 30+ ft of driving distance | Readable | YES | PENDING
D2 | Cabin: face recognition clear at 3 ft from camera | Clear | YES | PENDING
D3 | No frame drops or fisheye distortion on plates | No issues | — | PENDING
NIGHT VISION (CRITICAL)
N1 | Front: read a license plate of car in front at 20 ft after sunset | Readable not smeared | YES | PENDING
N2 | Cabin: driver's face visible WITHOUT cabin dome light on | Visible | YES | PENDING
N3 | No IR LED glare bouncing off windshield | Clean | — | PENDING
ELECTRICAL
E1 | Works on 12V outlet, no overheat after 30 min plugged in | OK after 30 min | YES | PENDING
E2 | Works on 24V semi outlet (if available to test) | OK no smoke/burn | YES | PENDING
SOFTWARE / LOOP
S1 | Loop recording overwrites old footage cleanly | Clean loop | YES | PENDING
S2 | G-sensor incident lock works when dash is slapped hard | Triggers lock file | YES | PENDING
S3 | Power-off → power-on resumes recording without setup | Auto-resume | — | PENDING
DECISION RULES
Night vision PASS + 24V (if claimed) PASS → ✅ LIST the SKU.
Night vision FAIL → try CJ-USA equivalent. Fail again → drop to single-channel front-only ($39.95).
24V FAIL (if supplier claimed dual-voltage) → drop SKU or reposition as 12V-only.
FINAL DECISION
Decision (LIST / TRY CJ / DROP):
Decision rationale (1–2 sentences):
Decision date:
Tested by: | Demarquis Hinton

## Charger
24V/12V Heavy-Duty USB-C + USB-A Charger
SKU: SRS-EM-001 | Supplier: Zendrop US (primary) / CJ-USA (backup)
Sample cost: $11.00 | Sell price: $24.95
Warehouse target: CA / NJ / GA US warehouse
ORDER TRACKING
Order placed (date):
Order # / tracking:
Arrived (date):
Days from order to arrival:
Test ID | Test description | Expected pass criteria | MUST PASS? | Result | Date tested | Notes
PACKAGING & BUILD
P1 | Arrived within 5 business days | 5 days or less | YES | PENDING
P2 | Product label printed on housing explicitly reads '12V/24V' or '12-24V DC' | Voltage label visible | YES | PENDING
P3 | Includes mounting hardware, weather cap, replaceable fuse | All accessories | — | PENDING
P4 | No solder splatter or loose internal parts when shaken | Clean build | — | PENDING
12V ELECTRICAL TEST
V1 | Plug into 12V outlet — both USB-C and USB-A power a phone | Both ports work | YES | PENDING
V2 | USB watt meter confirms ~30W PD on USB-C | ≥ 27W measured | YES | PENDING
V3 | USB watt meter confirms ~18W QC on USB-A | ≥ 15W measured | YES | PENDING
V4 | Plugged in for 30 min with phone charging — housing warm OK, hot = fail | Not hot to touch | YES | PENDING
24V ELECTRICAL TEST
T1 | Plug into 24V semi outlet — works no smoke no burn smell | Clean operation | YES | PENDING
T2 | If unable to test 24V, supplier provided UL/CE cert showing 12-24V range | Cert provided | YES | PENDING
DECISION RULES
12V/24V label PRESENT + electrical test PASS → ✅ LIST as 'Built for semi 24V systems.'
12V works but spec sheet is fuzzy / 24V not testable → reposition product page as 12V-only. Do not market for semi 24V systems.
Smoke / burn on 24V test → reject SKU entirely.
FINAL DECISION
Decision (LIST / TRY CJ / DROP):
Decision rationale (1–2 sentences):
Decision date:
Tested by: | Demarquis Hinton

## Headset
Trucker Bluetooth Headset — Single-Ear, Noise Canceling
SKU: SRS-EM-003 | Supplier: Zendrop US (primary) / CJ-USA (backup)
Sample cost: $23.00 | Sell price: $59.95
Warehouse target: CA / NJ / GA US warehouse
ORDER TRACKING
Order placed (date):
Order # / tracking:
Arrived (date):
Days from order to arrival:
Test ID | Test description | Expected pass criteria | MUST PASS? | Result | Date tested | Notes
PACKAGING & BUILD
P1 | Arrived within 5 business days | 5 days or less | YES | PENDING
P2 | Includes USB-C charging cable, soft pouch, optional ear hook | All accessories | — | PENDING
P3 | Boom mic rotates 180° (left ear ↔ right ear swap) | Full rotation | YES | PENDING
P4 | Power button has tactile click, no mush | Tactile feedback | — | PENDING
P5 | Charging port is USB-C (not Micro-USB) | USB-C confirmed | YES | PENDING
PAIRING
B1 | Pairs with first phone in ≤ 30 seconds | Quick pair | YES | PENDING
B2 | Pairs with second phone simultaneously — both stay connected | Dual-pair works | YES | PENDING
B3 | Voice prompts in English (Power on / Connected / Battery low) | English prompts | — | PENDING
CALL QUALITY (CRITICAL)
Q1 | 5-min call WHILE DRIVING with road noise — inbound clarity rated by listener 7+/10 | ≥ 7/10 rating | YES | PENDING
Q2 | Inbound voice you hear is clear at ~70% volume without distortion | Clear playback | YES | PENDING
BATTERY
BT1 | Full charge → continuous talk time measured | ≥ 15 hours real-world | YES | PENDING
BT2 | Charge time from empty to full | ≤ 3 hours | — | PENDING
COMFORT
C1 | Worn for 4 hours straight — no ear pain or headband pressure | Comfortable | — | PENDING
DECISION RULES
All MUST-PASS items clear → ✅ LIST.
Call quality < 7/10 OR battery < 15 hr → try CJ-USA equivalent.
CJ-USA also fails → drop SKU until v2; consider BlueParrott affiliate/reseller program.
FINAL DECISION
Decision (LIST / TRY CJ / DROP):
Decision rationale (1–2 sentences):
Decision date:
Tested by: | Demarquis Hinton

## Waterless Wash
Waterless Wash & Wax Kit + Microfibers
SKU: SRS-TC-001 | Supplier: Zendrop US (primary) / Spocket US (backup)
Sample cost: $17.00 | Sell price: $34.95
Warehouse target: US warehouse — confirm not aerosol
ORDER TRACKING
Order placed (date):
Order # / tracking:
Arrived (date):
Days from order to arrival:
Test ID | Test description | Expected pass criteria | MUST PASS? | Result | Date tested | Notes
PRE-IMPORT SUPPLIER ANSWERS
A1 | Formula type confirmed: PUMP SPRAY (not aerosol) | Pump spray | YES | PENDING
A2 | MSDS provided — no flammable solvents (no ethanol/methanol/naphtha) | Non-flammable | YES | PENDING
A3 | Product DOT-classified as non-hazardous for shipping | Non-haz cert | YES | PENDING
A4 | Bottle size confirmed (target: 32 oz for $34.95 price) | 32 oz | — | PENDING
A5 | Microfiber GSM rating ≥ 250 confirmed | ≥ 250 GSM | — | PENDING
PACKAGING & BUILD
P1 | Arrived within 7 business days | ≤ 7 days | YES | PENDING
P2 | Bottle sealed, no leaking | Sealed | YES | PENDING
P3 | Spray pump primes & sprays evenly (no clogging on first 5 pumps) | Clean spray | YES | PENDING
P4 | Microfiber towels are plush (≥ 250 GSM), no loose threading | Plush quality | — | PENDING
SHIPPING COMPLIANCE
S1 | Packaging label reads 'Not Hazardous' — no DOT diamond warning | Non-haz label | YES | PENDING
S2 | No UN number on packaging | No UN number | YES | PENDING
REAL-WORLD PERFORMANCE
R1 | Applied to dusty vehicle panel: clean, no streaks, no scratching | Streak-free, no scratch | YES | PENDING
R2 | Applied to chrome surface (bumper/exhaust): streak-free | Streak-free on chrome | YES | PENDING
R3 | Applied to glass: streak-free | Streak-free on glass | YES | PENDING
DECISION RULES
Pump spray + non-haz + clean wipe → ✅ LIST.
Aerosol OR contains flammables → REJECT (shipping restrictions kill the SKU).
Streaky / scratchy real-world performance → try CJ-USA, then drop if also fails. Pivot to a microfiber-only cleaning kit instead.
FINAL DECISION
Decision (LIST / TRY CJ / DROP):
Decision rationale (1–2 sentences):
Decision date:
Tested by: | Demarquis Hinton